## Sheet1
Group | Objective | Category | Milestones | Indicators | Status | Next Update
0 | Formalize a Roadmap and Monitoring System for Goal Alignment | Soft skills | Draft roadmap Q3 2025; Quarterly updates; Final review Q4 2026 | Roadmap document delivered; Quarterly updates completed; Feedback from manager | Not started | Q3 2025
1 | Develop and Deliver Internal Capacity-Building Activities | Contribution to LISER community | First presentation Q4 2025; Follow-up session Q2 2026 | Number of presentations delivered; Researcher feedback | Not started | Q4 2025
2 | Advise and Contribute to the Design of Technical Data Science Solutions | Technical or Administrative Excellence | Draft infrastructure proposal Q2 2026; Tool implementation Q4 2026 | Number of technical solutions proposed; Tools/services implemented | Not started | Q2 2026
3 | Publish and Disseminate Applied Research in AI | Scientific Excellence | Draft paper Q2 2026; Submission Q4 2026 | Number of papers submitted; Number of external presentations | Not started | Q2 2026
4 | Foster Strategic Collaborations in AI and Data Science | Societal Impact | Join 1 initiative Q2 2026; Present results Q4 2026 | Number of initiatives joined; Outcomes of collaborations | Not started | Q2 2026
5

## Sheet2
group | start date | end date | person | department | subject | comment | time | Status
1 | 2025-06-18 | 2025-07-17 | LISER | LC/LM/UDM | fNIRS workshop | Organized internal workshop | 10 | Finished
2 | 2025-07-01 | 2025-09-23 | Nikos Askitas | LM | Meluxina | access MeluXina | 2 | Finished
4 | 2025-07-01 | 2025-08-26 | LISER | LISER | Master Supervison | Supervision and defenses | 20 | Finished
2 | 2025-07-01 | 2025-12-09 | Eugenio Peluso | LC | EVOSS | Meetings, discussions, data | 25 | Finished
2 | 2025-07-01 | 2025-11-15 | Eugenio Peluso | LC | Allouer le contingent Ville de Luxembourg | data, report | 80 | Finished
3;4 | 2025-07-01 | 2025-09-25 | Thiago Brant | IS | AI4EDUCATION | Meetings, discussions, data | 16 | Finished
2 | 2025-07-03 | 2025-09-23 | Eugenio Peluso | LC | Stand Society in Motion | Request coordination and creation of the stand for LC | 60 | Finished
2 | 2025-07-03 |  | Thierry Kruten | IS | Code converter | SAS that you can use to evaluate AI converters | 6
2;4 | 2025-07-10 | 2025-12-07 | Thiago Brant | IS | AIDCO | Meetings, discussions, data | 15 | Finished
1 | 2025-07-18 | 2025-07-18 | Philippe Liegeois | LC | ChatGPT | help using the tool | 2 | Finished
2 | 2025-08-01 | 2025-09-16 | Kristell Leduc | LC | Observatoire Dudelange | translation, data request | 8 | Finished
2 | 2025-08-11 | 2025-09-22 | Julio Garbers | LM | Meluxina | Large memory request | 1 | Finished
2;4 | 2025-09-08 | 2025-09-19 | Catalina Lomos | LC | Dor Abrahamson visit | Help in the workshops | 80 | Finished
2;4 | 2025-09-11 | 2025-09-11 | Catalina Lomos | LC | LIST | Visit, discussion, grant proposal | 4 | Finished
2 | 2025-09-16 |  | Patrick bousch | LISER | Observatoire | meeting | 1
4 | 2025-09-24 | 2025-12-09 | Thiago Brant | LISER | Data Science Association | Invitation, booking and scheduling section for 31/10/2025 | 4 | Finished
4 | 2025-09-25 | 2025-12-05 | Christina Gathmann | LM | Phd supervision | Request to find a supervisor in DCC for her new Phd | 3 | Finished
2 | 01/01/205 |  | Christina Gathmann | LM | UPSKILL | WKP preparation and revision | 8
2 | 21/07/205 | 2025-07-31 | Maxence De Valière | RH | AI for HR | feasibility assessment | 10 | Finished
2 | 31/09/2025 |  | Bertrand Verheyden | LM | RISE - Digital | algorithm selection | 5
1 | 31/09/2025 | 31/09/2025 | Mattia Laudi | LM | Meluxina | Consulting | 0.5 | Finished
2 | 31/09/2025 | 2025-11-25 | Ludivine Martin | LM | OJV | Data analysis | 12 | Finished
2 | 2025-09-10 | 2025-09-12 | Thierry Kruten | IS | Meluxina | Contract and questions for Meluxina meeting | 8 | Finished
2 | 2025-10-01 |  | Alessio Fusco | LC | AI voice over | Create a sound clip with a specific narration | 4 | Finished
2 | 2025-10-02 |  | Thierry Kruten | IS | Restricted data | create a plan for access to Meluxina with restricted data | 4
3 | 2025-10-10 | 2025-12-05 | Thiago Brant | IS | fNIRS experiment | organize everything for the experiment | 36
4 | 2025-10-17 |  | Eugenio Peluso | LC | Partnership Dep. Computer Science | Organize meeting, identify research overlap | 4 | Finished
4 | 2025-10-21 | 2025-10-21 | Thierry Kruten | IS | Event with DFKI | Research guests, prepare slides, attend event | 4 | Finished
4 | 2025-11-08 | 2025-11-13 | Thierry Kruten | IS | Meluxina meeting | prepare meeting | 4 | Finished
4 | 2025-11-20 | 2025-11-25 | Christina Gathmann | LM | Wolfang Presentation | Prepare presenation for Wolfang | 16 | Finished
2 | 2025-11-12 | 12/112025 | Christina Gathmann | LM | DSS | DSS | 2 | Finished
2 | 2025-11-14 | 2025-11-14 | Eugenio Peluso | LC | BloomingAI | Participate in the meeting and discusss the project | 6 | Finished
1 | 2025-12-04 | 2025-12-04 | Thierry Kruten | IS | Google AI Agents Live Luxembourg | trainning | 8 | Finished
1 | 2026-01-04 | 2026-01-09 | Thierry Kruten | IS | NLDL Winter School | trainning | 40 | Finished
1 | 2026-01-12 |  | Thierry Kruten | IS | NLDL Winter School | Project | 24